# SWIFTECH SOLUTIONS
# PROPOSAL OF A MOBILE RESPONSIVE WEB-PAGE
# FOR NAIROBI BOOK-STORE
Prepared by: Dismas Imaya - Project Manager at SwifTech Solutions
Version 1
Date: 18th February, 2016

## OBJECTIVES
To develop a mobile responsive web page that is appealing to people of age between 16 to 30 years old for Nairobi book store that will enable them to showcase the books that they have off-line. The books cannot be distributed or read on-line but provide a view so that they may come physically to purchase. Additionally develop a blog for this website.

## TEAM
- Dismas Imaya, Project Manager (imayadismas@gmail.com)
- Antony Ng'anga, Front-End Developer (tonny.nesh@gmail.com)
- Evans Mwongera, Back-End Developer (evanmwongera@gmail.com)

## SCOPE OF WORK
A web page that will comprise of the following:
1. A mobile responsive website
2. A landing page for the book store.
3. The website should allow book store to showcase the books they have off-line.
4. The users should be able to like, and rate the books and the authors.
5. The site should enable the users to send an email concerning a given book they have showcased on-line.
6. The site should be able to have automatic updates as soon as the do an update on their book shelves.
7. The site should not allow one to read nor buy the book on-line.
8. A blog that will allow the book store to post articles on the books that they offer.
## TIME-LINE
Activity	Date	Details	Deliverables
A meeting with the Nairobi Book-Store Manager	22nd February 2016 / at 2.00 PM	Discuss with the client to clarify on some sections of the project and collection of the resources to be used.	Meeting
Internal meeting with all the teams that will take part on the project	23rd February 2016	Aligning every team with the project
The design team meeting and doing research on how the website and blog.	24th to 26th February 2016	Come up with a model and present it to the clients and anticipate for the feedback.	Crude Design Model of the Website and Blog
The design team meeting to finalize.	1st - 5th March 2016	Develop a refined design model developed considering the feedback received.	Refined Design Models
Development of the landing page and blog	8th - 11th March 2016	Complete the front end development using the model developed.	Landing Page and Blog complete
An internal meeting for progress tracking.	12th March 2016	Do an assessment of the project progress and determine whether the goal has been achieved	Internal
Design of the Database architecture	15th March 2016	Come up with a database model on how the data will be stored and retrieved from the entities	Database Model
Develop the back end of the website	16th – 30 March 2016	Complete the back- end of the website such that it can retrieve, delete, update and add data to the database	Business Logic of the website
An internal meeting for progress tracking.	31st March 2016	Do an assessment of the project progress and determine whether the goal has been achieved	Internal
Do system testing	1st to 2nd April 2016	Carry out a comprehensive system testing on the website and blog based on the functional and non functional requirements.	High-Level Prototype
Evaluation of the website and blog	5th April 2016	Presenting the clients the whole website and blog and give it to users for usability testing.	Usability Problems.
Usability problems and errors fixing	6th - 9th April 2016	Fixing the Usability problems and errors that may have been overlooked	An Error Free Website and blog
Delivery of the website and blog	12th April 2016	Deployment of the website and the blog on the client's domain.	Completed Project

## PROJECT COSTS
ACTIVITY	AMOUNT	NOTES
Front – end	200, 000	Landing Page, Foundation framework, HTML5	and CSS3, JavaScript
Back end	300,000	Business Logic, Python, Django and Node js
Blog	150, 000	Blog using Django and Python
TOTAL	650,000

GROSS TOTAL + VAT	700, 000
We would like to get a down payment of 50% before we embark on the actual project initiation to facilitate our plan and smooth execution of the project initial resources.

## SIGNATURES
Development Company	Nairobi Book-store

Name__________________________________Name____________________________________

Position ________________________________Position__________________________________

Signature________________________________Signature________________________________

Date____________________________________Date____________________________________